## Project Progress
PROJECT STATUS REPORT
PROJECT INFORMATION
Project Name | Service Centre Management (Calling)
Date of Report | 2025-01-24
Project Date of Starting | 2025-01-20
Projected Date of Completion | 2025-02-01
Project Manager | Mr. Arora; eGAIN
PROJECT STATUS
Overall Project Status | In progress
Summary
PROJECT DETAILS
TASK | TEAM MEMBERS |  | STATUS | DATE | NOTES
| Vandana Subramanian | Ambuj Mishra
Project Report | Project overview |  | In Progrss | 2025-01-21 | Delayed by a day
GUI in Tkinter | 30 Tkinter screens | 20 Tkinter screens | Complete | 2025-01-23 | Completed task on time
MySql Database Connectivity | 30 screens | 20 screens | Complete | 2025-01-23 | Completed task on time
Database in MongoDB | SCM database and collection created |  | Complete | 2025-01-23
GitHub Repository | GitHub login created |  | On-going | 2025-01-24 | Files uploaded on GitHub
Project Status Report | Progress and task allocation sheet |  | On-going | 2025-01-24
Dashboard Creation
Form Fields Validation
Debugging
Testing